Research Proposal

NAME: Miguel Alfonso Flores Sánchez

PROPOSAL TITLE: Trustworthy Graph-Functional AI for Cyber-Physical Anomaly Detection in Critical Infrastructures (GRAIL-ORI)

RESEARCH TOPIC: Advanced AI for Cybersecurity, Defence and Anomaly Detection in Critical Infrastructures.

HOSTING INSTITUTION: Universidade da Coruña (UDC), CITIC

SELECTED SUPERVISOR: Salvador Naya Fernández

# EXCELLENCE

## Description of the state of the art and problem identification

Critical infrastructures, including water and energy systems, industrial installations, transport networks, smart buildings and digital services, increasingly operate as interconnected cyber-physical systems. Their condition is observed through heterogeneous streams from sensors, actuators, control platforms and communication devices. Abnormal behaviour may arise from equipment degradation, sensor malfunction, communication disruption, unexpected operating conditions or deliberate manipulation. Early detection is therefore central to cybersecurity, continuity of service and infrastructure resilience.

Functional Data Analysis (FDA) provides interpretable representations of smooth, irregular and densely sampled trajectories, while functional statistical process monitoring supports statistically defined alarms [1,2]. These methods, however, usually analyse assets independently and do not explicitly represent the physical, logical or communication relationships that connect them. Deep anomaly-detection methods learn nonlinear patterns from high-dimensional data, yet rare and poorly labelled events, class imbalance and changing operating regimes remain difficult [3]. Graph-based approaches model relational structure and can identify abnormal nodes, edges or subgraphs [4,5], but many reduce temporal information to fixed windows, offer limited false-alarm calibration and generate explanations whose reliability is seldom tested.

The gap is especially important in critical infrastructures, where cyber-induced changes to measurements, control actions or communications may resemble ordinary failures. Water-distribution benchmarks have shown that attacks can be detected and affected components localised from operational telemetry [6,7]. Even so, continuous trajectories, infrastructure topology, statistical monitoring, calibrated uncertainty and reliable explanations are rarely handled within one coherent framework.

Problem identification. Current methods do not provide a statistically grounded way to detect, localise and explain anomalies across continuous cyber-physical signals and interconnected assets under realistic conditions. Measurements may be noisy, irregular or missing; labels may be incomplete; topology and operating regimes may evolve; and similar deviations may reflect faults, communication disturbances or potentially malicious activity. High average accuracy is insufficient if a model produces excessive false alarms, fails across operating periods or cannot identify the relevant component, variable and time interval. An anomaly score should therefore support investigation, not be treated as conclusive evidence of a cyberattack.

GRAIL-ORI addresses this problem through a trustworthy graph-functional AI framework that jointly models multivariate trajectories and infrastructure relationships, combining functional statistical monitoring, graph representation learning, self-supervised anomaly detection, robust scoring, uncertainty calibration and multi-level explanations.

Central research question. How can continuous operational observations and graph-structured dependencies be jointly modelled to provide accurate, calibrated and explainable detection of cyber-physical anomalies under scarce labels, noisy measurements and evolving infrastructure conditions?

Global objective. To develop and validate a trustworthy graph-functional AI framework that transforms multimodal infrastructure data and physical, logical or communication dependencies into accurate, calibrated and explainable anomaly intelligence.

Specific objectives. O1: prepare two complementary critical-infrastructure datasets and one controlled simulation benchmark, with an anomaly taxonomy, dataset cards and a preregistered protocol by M7 (D2.1, MS1). O2: develop a graph-functional detector and compare it with at least eight statistical, machine-learning and deep-learning baselines by M15 (D3.1, MS2). O3: integrate calibrated uncertainty and explanations at component, relational, variable and temporal levels, targeting calibration error no greater than 0.05, or coverage within five percentage points of the nominal level, and explanation stability of at least 0.75 by M20 (D4.1, MS3). O4: validate the framework in two complementary infrastructure contexts and release a documented toolkit and demonstrator by M27 (D5.1, D5.2, MS4).

Ambition beyond the state of the art. GRAIL-ORI will treat networked functional trajectories as first-class analytical objects rather than simply combining FDA with graph neural networks. Continuous-time and multiresolution representations will enter topology-aware learning directly, while alerts will include calibrated uncertainty and quantitatively assessed explanations. Because visually plausible graph explanations may be unreliable [8], fidelity and stability will be tested before explanations are used as evidence. The project thus advances from isolated black-box scores to reproducible anomaly intelligence that indicates whether abnormal behaviour is occurring, where it originates, how it relates to connected assets and how reliable the evidence is.

## Methodology and originality of the proposed research project

Overall methodology. The project follows a modular, benchmark-driven sequence aligned with O1-O4: data and benchmark preparation; graph-functional model development; uncertainty calibration and explanation; and cross-context validation. Each stage produces a usable output and a decision point, allowing the work to proceed with a simpler statistical or hybrid model if added complexity does not yield reproducible value.

For O1, two complementary application datasets and one controlled simulator will combine multivariate process or sensor telemetry with physical, logical or communication dependencies; communication and network-flow information will be incorporated where available. Naturally observed, controlled and synthetic events will be distinguished. Each system will be represented as a dynamic attributed graph whose nodes correspond to assets, sensors, control devices or subsystems and whose edges encode known or constrained data-driven relationships. Penalised splines, wavelets and related multiresolution tools will transform irregular or noisy measurements into functional representations. All preprocessing will be estimated on training periods only. Dataset cards will document provenance, missingness, event definitions, graph construction and topology uncertainty, and the evaluation protocol will be preregistered by M7.

For O2, the framework will integrate a functional encoder, a temporal graph module, self-supervised prediction or reconstruction, and robust anomaly scoring and localisation. Known infrastructure relationships will be prioritised, while learned graphs will be constrained for sparsity and checked against domain knowledge. The model will be compared with functional monitoring, one-class, reconstruction-based, temporal and graph-based baselines. Ablation studies will identify the contribution of functional representation, graph structure, self-supervision and robust scoring.

Initial dataset strategy. BATADAL, SWaT and WADI will be considered as initial candidate benchmarks for developing and validating the graph-functional framework. They will support the analysis of operational telemetry, infrastructure dependencies, anomaly detection, localisation and uncertainty-aware evaluation.

For O3, dependence-aware bootstrap procedures and conformal methods will be used to quantify uncertainty and calibrate anomaly scores. Explanations will combine functional contributions, graph attribution and perturbation analysis to identify influential components, relationships, variables and time intervals. Their fidelity, sparsity, stability and sensitivity to data or topology perturbations will be evaluated quantitatively; unreliable explanations will be simplified or withheld.

For O4, the selected framework will be tested in at least two complementary critical-infrastructure contexts using temporally separated development and test periods. Assessment will cover event detection and localisation, false alarms, delay, calibration, missing observations, topology perturbations, computational cost and explanation reliability. Repeated blocked validation, uncertainty intervals and sensitivity analyses will support robust conclusions. The final toolkit and demonstrator will be evaluated with specialists as decision-support instruments; they will not perform autonomous control or definitive attack attribution.

Interdisciplinarity. GRAIL-ORI integrates FDA, nonparametric inference, statistical process monitoring, graph machine learning, cybersecurity, infrastructure engineering, research software engineering and high-performance computing. Functional statistics preserve continuous temporal structure; graph learning represents dependencies and possible propagation; statistical inference supplies robust thresholds and uncertainty; cybersecurity and infrastructure knowledge guide realistic scenarios and interpretation; and software engineering and HPC support scalable, reproducible experimentation. These disciplines are combined within one workflow rather than developed as separate strands.

Originality and innovative aspects. The project contributes a graph-functional representation of continuous telemetry and infrastructure relationships; a hybrid detector combining learned graph representations with robust functional evidence; dependence-aware uncertainty and calibration; explanations evaluated jointly at component, relational, variable and temporal levels; and a modular implementation designed for reproducible comparison and transfer. Its originality lies in combining statistical rigour, network structure and a human-centred design into a single framework, rather than simply putting existing methods side by side.

Gender dimension and diversity. The core research objects are machine-generated telemetry, infrastructure components and system events; sex and gender do not determine the mechanisms generating these data and are not scientifically relevant variables for the core models. Diversity remains relevant to evaluation and deployment because geographic coverage, infrastructure quality, sensor density or data availability may create unequal monitoring performance. These differences will be examined where the case studies permit. Expert activities will seek diversity in role, seniority and gender, and any future use of personal data will require a renewed ethics, gender and data-protection assessment.

Open Science. A Data Management Plan will define metadata, storage, access, retention, licensing and preservation. FAIR principles will apply to outputs that can be shared legally and securely. Public and synthetic data will be documented through dataset cards and persistent identifiers; version-controlled code, documented splits, containers, model cards and archived releases will support reproducibility. Publications will be openly accessible where possible. Sensitive operational data, network topologies and security-relevant information will follow the principle “as open as possible, as closed as necessary”; when raw data cannot be released, metadata, schemas, synthetic alternatives and evaluation protocols will be shared when safe. Negative findings, limitations and computational costs will also be reported.

## Fit between the project and the host organisation / research group

Applicant-project fit. My research background in FDA, nonparametric and bootstrap inference, statistical process monitoring and anomaly detection directly supports the project’s functional representation, robust monitoring and uncertainty components. Recent work on graph neural networks and spatio-temporal modelling, multimodal integration, IoT security and botnet detection adds experience with relational systems and cybersecurity-oriented evaluation. I also bring practical skills in R, Python, SQL and deep-learning frameworks, together with reproducible software development, project leadership, supervision and academic management.

Host and supervisor fit. UDC, CITIC and the MODES research group provide a strong setting for GRAIL-ORI. Prof. Salvador Naya Fernández’s expertise in FDA, statistical process control, nonparametric statistics, reliability and industrial monitoring is closely aligned with the project’s statistical foundations. Our previous collaboration reduces start-up time, while CITIC adds complementary expertise in AI, cybersecurity, intelligent networks and HPC needed to extend the work towards graph-based cyber-physical monitoring.

Two-way transfer of knowledge. I will transfer functional statistical monitoring, bootstrap inference, robust anomaly detection, reproducible R/Python components, teaching and supervision experience, and links with Ecuadorian and Latin-American networks. Through supervision, CITIC and MODES seminars, joint experiments and UDC support services, I will acquire advanced graph anomaly detection, cybersecurity-oriented validation, trustworthy AI, secure ML pipelines, GPU-enabled experimentation, European project management and exploitation skills. An internal tutorial and reusable functional-data components will turn this exchange into concrete host benefits.

Collaborations and secondment. Collaboration across CITIC will support graph-architecture review, threat-informed scenarios, network-aware validation and secure experimental pipelines. A two-month secondment at CESGA is planned for M21-M22, subject to formal confirmation, to optimise sparse graph-functional workflows, profile scalability and energy use, and integrate a portable HPC workflow into the final toolkit. Its timing places the secondment after core model selection and before final demonstrator release, adding complementary computational skills without placing the project’s core objectives at risk.

# IMPACT

## Expected impact of the fellowship on the applicant’s career development

Career objectives. Within five years of the fellowship, I aim to lead an internationally visible research line in trustworthy graph-functional AI for cyber-physical anomaly detection, supported by maintained software, strong publications, postgraduate supervision and competitive European or international proposals. In the longer term, I intend to coordinate a stable network linking Galicia, other European environments and Latin America around secure, resilient and human-centred monitoring systems.

My main objective remains a leadership career in research and higher education. The same competences will also strengthen my suitability for senior roles in technology centres, public-sector innovation units, critical-infrastructure organisations and research-intensive companies, particularly in R&D management, technology transfer and advanced analytics.

Scientific independence and skills. TALENTGAL will convert my experience in teaching, supervision, project leadership and academic management into a coherent applicant-led programme. I will take responsibility for research design, benchmark definition, methodological choices, software, validation, publications, stakeholder engagement and exploitation. Training will develop scientific skills in dynamic graphs, self-supervised anomaly detection, calibration and explanation evaluation; technical skills in GPU/HPC experimentation, scalable graph processing and reproducible software; and transferable skills in European project leadership, intellectual property, communication and stakeholder engagement.

A Career Development Plan will be reviewed at M2, M12, M24 and M30 using indicators for publications, software, training, networking, stakeholder engagement and future applications. By M30, I will have a five-year research agenda, an expanded European and intersectoral network, and at least one follow-on funding or collaboration proposal.

## Dissemination, exploitation plan and communication activities.

Dissemination. The project will address researchers in FDA, statistical process monitoring, graph learning, trustworthy AI, cybersecurity and infrastructure analytics. It will target at least three open-access manuscripts and four contributions to international conferences, workshops or seminars. Software, synthetic benchmarks, evaluation protocols, model and dataset cards and reproducible configurations will be deposited in trusted repositories with persistent identifiers where appropriate. Researchers will receive methodological detail, while operators and technology organisations will receive benchmark evidence and implementation guidance, and policymakers will receive concise material on resilience, human oversight and the limitations of automated detection.

Exploitation. Four initial Key Exploitable Results are foreseen: a graph-functional representation and benchmark protocol; the modular detection library; an uncertainty, robustness and explanation-evaluation toolkit; and a decision-support demonstrator with implementation guidance. UDC knowledge-transfer services will assess maturity, ownership, security restrictions and target users. Routes may include open-source adoption, training, technical services, proof-of-concept studies, sector adaptation, collaborative pilots and follow-on proposals. Claims will remain evidence-based: the fellowship will demonstrate feasibility and prepare uptake, not assert large-scale deployment or financial savings.

Intellectual property. Background data, software and knowledge will retain their existing ownership. New results will be reviewed before disclosure under UDC rules and collaboration agreements. Copyright and open-source licensing will be the default for non-sensitive software, documentation and research objects; confidentiality, controlled licensing or protected know-how may be used for security-sensitive or sector-specific components. Patent protection will be considered only if novelty, inventive character, practical applicability and a credible route to use are demonstrated. Sensitive vulnerabilities and operational configurations will not be disclosed without institutional assessment.

Communication and engagement. A bilingual project webpage, at least six accessible outputs, participation in CITIC, UDC and TALENTGAL outreach, two stakeholder workshops, one open demonstration and one policy or implementation brief will address students, citizens, professionals and public-sector audiences. Early engagement will refine requirements; later engagement will test usability and explanation clarity. Materials will use inclusive language, protect sensitive details and distinguish anomaly evidence from confirmed cyberattack attribution.

## Expected scientific, societal and economic impact

Scientific impact. GRAIL-ORI will establish a reproducible bridge between functional statistics, process monitoring, graph learning and trustworthy AI. The graph-functional representation, hybrid detector, calibrated alerts, explanation-evaluation procedures and benchmark protocols will be reusable in systems where continuous signals interact through physical, logical or communication networks. Open software and documented workflows will improve comparability and support further work on topology uncertainty, anomaly propagation and calibration drift.

Economic and technological impact. The toolkit and demonstrator will integrate process telemetry, relational dependencies, uncertainty and traceable explanations. More reliable and localisable alerts may reduce alarm overload, accelerate investigation and support condition-based maintenance. Performance will be assessed through false alarms, delay, localisation, calibration, computational efficiency and expert feedback. The modular implementation will lower technical barriers for research centres, public operators, technology providers and SMEs, and may support future services, pilots or sector-specific integration in water, energy and other cyber-physical infrastructures.

Societal and environmental impact. Earlier and more proportionate investigation of faults, communication disruptions and cyber-induced disturbances may strengthen the continuity of essential services and public confidence in AI-assisted monitoring. Human experts will retain responsibility for interpretation and response. Earlier identification of inefficient operation or equipment degradation may reduce unnecessary energy, materials and interventions; computational cost will also inform model selection. Where data permit, the project will report differences in monitoring quality associated with geographic coverage, infrastructure condition or sensor availability, supporting more transparent and inclusive use.

Long-term pathway. Validated methods will move from reproducible evidence to an open toolkit and demonstrator, specialist assessment, and realistic routes for collaboration, pilots, services or follow-on funding. Longer-term impact will be indicated by publications, software reuse, benchmark uptake, stakeholder participation and new research or transfer activities.

# IMPLEMENTATION

## Work plan and implementation

GRAIL-ORI is organised into six interdependent Work Packages over 30 months. WP2-WP5 correspond to O1-O4; WP1 provides governance; and WP6 integrates training, career development, secondment, dissemination, communication and exploitation. Formal reviews at M7, M15, M20 and M27 control progression and activate fallback routes when required.

WP1: Project management, ethics and data governance. Duration: M1-M30. Goal: Ensure timely, ethical, secure and high-quality delivery. Tasks and endpoint: T1.1 coordinates progress, resources and risks; T1.2 establishes and reviews the Career Development Plan; T1.3 implements the Data Management Plan, FAIR procedures and research integrity; T1.4 monitors ethics, cybersecurity, human oversight and responsible disclosure. WP1 supports every technical WP and triggers corrective action. Outputs: D1.1 Career Development Plan, M2 with reviews at M12, M24 and M30; D1.2 Data Management Plan, M3 and update M18; MS0 governance operational, M2.

WP2: Data engineering and graph-functional benchmark. Duration: M1-M7. Goal: Deliver the data, anomaly taxonomy, graph structures and evaluation protocol required for O1. Tasks and endpoint: T2.1 defines operational, communication-related and cyber-induced scenarios; T2.2 prepares two application datasets, including network-flow information where available; T2.3 develops functional preprocessing and graph construction; T2.4 builds the controlled simulator; T2.5 implements initial baselines and preregisters evaluation. The endpoint is a validated benchmark for WP3-WP5. Outputs: D2.1 benchmark, dataset cards, taxonomy, simulator and protocol; MS1 benchmark ready, M7.

WP3: Graph-functional anomaly-detection models. Duration: M4-M15. Goal: Develop and select the core framework required for O2. Tasks and endpoint: T3.1 develops functional and multiresolution representations; T3.2 models static and dynamic dependencies; T3.3 implements self- and semi-supervised learning; T3.4 develops robust scoring and localisation; T3.5 compares at least eight baselines and performs ablations. The selected model proceeds to WP4 and WP5. Outputs: D3.1 prototype, benchmark report and reproducible experiments; MS2 model-selection criteria met, M15.

WP4: Uncertainty, explainability and trustworthy AI. Duration: M9-M20. Goal: Add calibrated uncertainty, reliable explanations and responsible-use safeguards required for O3. Tasks and endpoint: T4.1 develops dependence-aware bootstrap inference; T4.2 investigates conformal calibration and drift; T4.3 generates component, relational, variable and temporal explanations; T4.4 evaluates fidelity, stability and robustness; T4.5 documents limitations and human-oversight conditions. Validated components are transferred to WP5. Outputs: D4.1 calibrated and explainable framework, model card and evaluation report; MS3 trustworthiness criteria met, M20.

WP5: Validation, software integration and demonstrator. Duration: M15-M27. Goal: Validate transferability and complete O4. Tasks and endpoint: T5.1 validates multivariate process telemetry; T5.2 performs communication-aware and network-traffic validation in a complementary context; T5.3 tests missing data, operating shifts and topology perturbations; T5.4 conducts expert review and error analysis; T5.5 integrates the toolkit and demonstrator, including CESGA optimisation results. Outputs: D5.1 validation, robustness and computational report, M25; D5.2 toolkit, demonstrator and guide; MS4 demonstrator validated, M27.

WP6: Training, secondment, dissemination and exploitation. Duration: M1-M30. Goal: Strengthen competence, visibility and longer-term use. Tasks and endpoint: T6.1 covers graph anomaly detection, trustworthy AI, software and European leadership; T6.2 delivers the CESGA secondment in M21-M22; T6.3 produces open-access publications and scientific contributions; T6.4 implements the webpage, outreach and workshops; T6.5 assesses KERs, IP and follow-on routes. Activities feed WP3-WP5 and the Career Development Plan. Outputs: D6.1 integrated training and impact plan, M4 and update M18; D6.2 secondment/HPC report, M23; D6.3 career and exploitation roadmap; MS5 secondment complete, M22; MS6 follow-on route defined, M30.

Implementation logic. WP2 fixes the evidence base before model selection; WP3 supplies the core detector; WP4 adds the conditions required for trustworthy use; and WP5 validates and integrates the final solution. Reviews at M7, M15, M20 and M27 determine whether to continue with the preferred architecture or use a simpler statistical, hybrid or non-relational alternative.

## Suitability of the host group, research environment and infrastructure

The Universidade da Coruña, through CITIC and the MODES research group, provides an appropriate environment for GRAIL-ORI. MODES contributes expertise in Functional Data Analysis, statistical process control, nonparametric methods and anomaly detection. CITIC complements this foundation through its research areas in Artificial Intelligence, Data Science and Engineering, High-Performance Computing, and Intelligent Networks and Services, together with cross-disciplinary Cybersecurity. Its research priorities include machine-learning methods for anomalous-situation detection and the use of HPC for data-intensive AI applications.

The work plan will use these capacities progressively. WP2 will draw on MODES expertise for functional preprocessing, anomaly taxonomy and statistical validation. WP3 and WP4 will use CITIC’s AI, cybersecurity and network-oriented environment for graph learning, trustworthy-AI assessment and communication-aware scenarios. CITIC’s physical and virtualised server infrastructure will support data processing, model training, reproducible experimentation and software integration. Seminars, methodological exchanges and interaction with researchers across CITIC will also support interdisciplinarity, training and expert review throughout WP1-WP6. No essential resource beyond the host’s current scientific and computational capacity is required. The core objectives will rely on open or research-accessible datasets and synthetic alternatives, avoiding dependence on proprietary infrastructure. If larger-scale computation is required, access will be requested through CESGA, whose services are available to researchers from Galician universities and include HPC, GPU and high-performance storage resources. The planned M21-M22 secondment, subject to formal confirmation, will provide additional support for scalability, portability and energy-efficiency profiling before release of the final toolkit and demonstrator.

## Risk assessment and mitigation measures

Risk management will be integrated into WP1 through a living risk register, regular researcher-supervisor reviews and formal stage-gate assessments at M7, M15, M20 and M27. Corrective action will be triggered by delays in essential resources, failure to meet predefined acceptance criteria, or ethical, security or computational constraints affecting the critical path.

R1. Limited or delayed access to operational data (medium likelihood, high impact). Open and research-accessible benchmarks will be prioritised, restricted access requested at project start, and modular data adapters prepared. If access remains unresolved by M4, the affected dataset will be replaced by an open equivalent or the controlled simulation benchmark. No core objective will depend on one proprietary source.

R2. Scarce, imbalanced or uncertain anomaly labels (high likelihood, medium impact). Self-supervised, semi-supervised and reconstruction-based learning will reduce dependence on labelled events, while natural, controlled and synthetic anomalies will be evaluated separately. If verified labels are insufficient, validation will focus on normal-behaviour modelling, controlled fault injection and simulated scenarios, with limitations reported transparently.

R3. Incomplete, uncertain or changing graph topology (medium likelihood, high impact). Physical, logical, communication-based and sparsity-constrained learned graphs will be compared through sensitivity and perturbation analyses. If relational information is unreliable, the project will retain a simplified graph or the strongest non-relational model and explicitly quantify topology uncertainty.

R4. The graph-functional model does not outperform simpler baselines or transfer across contexts (medium likelihood, high impact). Temporal validation, regularisation, ablation studies and comparison with at least eight baselines will prevent unjustified complexity. If the target architecture fails the M15 criteria, the strongest reproducible statistical, hybrid or non-relational alternative will proceed to WP4 and WP5. The project will still deliver validated evidence on when graph-functional complexity is beneficial.

R5. Calibration or explanations fail reliability criteria (medium likelihood, high impact). Bootstrap and conformal alternatives will be compared, and explanation fidelity and stability will be tested under data and topology perturbations. Unstable thresholds will be recalibrated; unreliable explanations will be simplified or suppressed. The demonstrator may therefore provide calibrated detection and localisation without unsupported explanatory claims.

R6. Computational, integration or scheduling constraints threaten completion (medium likelihood, high impact). Sparse computation, profiling, modular interfaces, CITIC resources and the planned CESGA secondment will support efficient implementation. If resource demand or delays exceed projections, model size, graph resolution and optional experiments will be reduced, prioritising the benchmark, selected detector, trustworthy-AI components, toolkit and demonstrator.

Ethics, confidentiality and limited specialist participation will also be monitored. Sensitive data will be replaced by anonymised, aggregated or synthetic alternatives where necessary, while expert validation can be completed through a smaller structured panel and scenario-based assessment.

R1, R3, R4, R5 and R6 are the critical risks because they may interrupt progression between O1-O4. Their contingency routes preserve a coherent and achievable project through alternative data, simplified topology, validated baseline models and reduced optional scope.

# GANTT CHART

Thirty-month schedule integrating the six Work Packages, deliverables, milestones, training, the CESGA secondment, dissemination, communication and exploitation.

|  |  | Year 1 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WP | Title | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| WP1 | Management and governance |  | D1.1 MS0 | D1.2 |  |  |  |  |  |  |  |  | R |
| WP2 | Data and benchmark |  |  |  |  |  |  | D2.1 MS1 |  |  |  |  |  |
| WP3 | Graph-functional models |  |  |  |  |  |  |  |  |  |  |  |  |
| WP4 | Trustworthy AI |  |  |  |  |  |  |  |  |  |  |  |  |
| WP5 | Validation and demonstrator |  |  |  |  |  |  |  |  |  |  |  |  |
| WP6 | Training, career and secondment |  |  |  | D6.1 |  |  |  |  |  |  |  |  |
| ACT | Dissemination, communication and exploitation |  | C |  |  |  |  |  | W |  |  |  |  |

|  |  | Year 2 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WP | Title | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 |
| WP1 | Management and governance |  |  |  |  |  | D1.2u |  |  |  |  |  | R |
| WP2 | Data and benchmark |  |  |  |  |  |  |  |  |  |  |  |  |
| WP3 | Graph-functional models |  |  | D3.1 MS2 |  |  |  |  |  |  |  |  |  |
| WP4 | Trustworthy AI |  |  |  |  |  |  |  | D4.1 MS3 |  |  |  |  |
| WP5 | Validation and demonstrator |  |  |  |  |  |  |  |  |  |  |  |  |
| WP6 | Training, career and secondment |  |  |  |  |  | D6.1u |  |  | S | S MS5 | D6.2 |  |
| ACT | Dissemination, communication and exploitation |  |  |  |  |  | C |  | W |  |  |  |  |

|  |  | Year 3 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| WP | Title | 25 | 26 | 27 | 28 | 29 | 30 |
| WP1 | Management and governance |  |  |  |  |  | D1.1f |
| WP2 | Data and benchmark |  |  |  |  |  |  |
| WP3 | Graph-functional models |  |  |  |  |  |  |
| WP4 | Trustworthy AI |  |  |  |  |  |  |
| WP5 | Validation and demonstrator | D5.1 |  | D5.2 MS4 |  |  |  |
| WP6 | Training, career and secondment |  |  |  |  |  | D6.3 MS6 |
| ACT | Dissemination, communication and exploitation |  |  | C |  |  | KER |

Legend: shaded = active; D = deliverable; MS = milestone; R = review; S = CESGA secondment; C = communication; W = stakeholder workshop; KER = exploitable-result review.

References

[1] Ramsay, J.O.; Silverman, B.W. Functional Data Analysis. 2nd ed. Springer, 2005. doi:10.1007/b98888.

[2] Flores, M.; Naya, S.; Fernández-Casal, R.; Zaragoza, S.; Raña, P.; Tarrío-Saavedra, J. Constructing a Control Chart Using Functional Data. Mathematics 2020, 8, 58. doi:10.3390/math8010058.

[3] Pang, G.; Shen, C.; Cao, L.; van den Hengel, A. Deep Learning for Anomaly Detection: A Review. ACM Computing Surveys 2021, 54, Article 38. doi:10.1145/3439950.

[4] Ma, X.; Wu, J.; Xue, S.; Yang, J.; Zhou, C.; Sheng, Q.Z.; Xiong, H.; Akoglu, L. A Comprehensive Survey on Graph Anomaly Detection With Deep Learning. IEEE TKDE 2023, 35, 12012-12038. doi:10.1109/TKDE.2021.3118815.

[5] Deng, A.; Hooi, B. Graph Neural Network-Based Anomaly Detection in Multivariate Time Series. AAAI 2021, 35, 4027-4035. doi:10.1609/aaai.v35i5.16523.

[6] Taormina, R. et al. Battle of the Attack Detection Algorithms: Disclosing Cyber Attacks on Water Distribution Networks. JWRPM 2018, 144, 04018048. doi:10.1061/(ASCE)WR.1943-5452.0000969.

[7] Taormina, R.; Galelli, S. Deep-Learning Approach to the Detection and Localization of Cyber-Physical Attacks on Water Distribution Systems. JWRPM 2018, 144, 04018065. doi:10.1061/(ASCE)WR.1943-5452.0000983.

[8] Agarwal, C.; Zitnik, M.; Lakkaraju, H. Probing GNN Explainers: A Rigorous Theoretical and Empirical Analysis of GNN Explanation Methods. AISTATS, PMLR 151, 8969-8996, 2022.

Generative AI disclosure. ChatGPT was used for language editing, structural condensation and consistency checks. All scientific claims, numerical targets and references were independently reviewed and verified by the applicant against the cited sources. The applicant acknowledges that generative AI may introduce bias, errors, omissions or inaccurate references and assumes full responsibility for the final content.